## Feature Checklist
Done? | Phase | Area | Feature | What it does | Status | Suggested person | Depends on | Done when
| P0 | Foundations | Freeze data contracts | Lock the shared shapes (action, directory, etc.) both halves build to | In progress | P1 | - | All shared shapes agreed; changes need both owners
| P0 | Foundations | 4 authority tiers | Operator / Lead / Member / Guest over Mattermost roles | In progress | P1 | - | A Member cannot approve; a Lead can
| P0 | Foundations | Branding (Agora) | Fork rebrand: plugin id + name + logo/wordmark + login + favicon all read Agora | In progress | P1 | - | No 'Mattermost' wordmark shows post-login
| P0 | Foundations | Fork Mattermost (own it) | Build Agora from a Mattermost source fork, not the stock image; we can change anything | In progress | P1 | - | Agora builds from our fork; all MM features still work
| P0 | Foundations | Keep all MM features | Every native Mattermost feature stays present and usable | In progress | P1 | fork | No MM feature is lost when adding Agora
| P0 | Foundations | Modular Agora layer | Agora features as clean, removable modules over the MM core | In progress | P1 | fork | A module can be removed without breaking MM
| P0 | Foundations | Tab-based app shell | Channel tab strip + RHS Agora tabs + collapsible sidebar | In progress | P1 | fork | Shell is canonical; dinosaur/master split resolved
| P0 | Foundations | Ordered navigation | First-run order: Settings -> Onboarding -> Channels | Planned | P1 | tab shell | New member is guided in order, never lost
| P0 | Foundations | Settings panel | In-app Agora settings (today the plugin schema is empty) | Planned | P1 | tab shell | Admin configures Agora in-app, not Docker env
| P0 | Foundations | Bot-dedicated channels | Channels owned by a specific bot/role, laid out in the shell | Planned | P1 | tab shell + roles | A channel binds to a bot/role in the shell
Y | P1 | The Room | Action cards | AI work shows as a rich card: main action + expandable sub-steps, live | Built | P1 | contracts | Posting an action renders rich + collapsible, not raw text
Y | P1 | The Room | Slash commands | /wrap /approve /pause /ai /claim | Built | P1 | - | Each command fires the right action
Y | P1 | Agents | Connector | Outbound connection, listens, replies in-thread, auto-reconnect | Built | P2 | - | Human<->AI in a live thread, verified
Y | P1 | Agents | AI adapters | Run Claude / Codex / Gemini headless with per-tool quirks | Built | P2 | connector | All three answer in the room
Y | P1 | Agents | Many bots per person | One owner can connect several AIs, each its own bot | Built | P2 | adapters | One person, multiple online bots
Y | P1 | Connecting | Pairing wizard | One-time code mints a bot + token | Built | P2 | authority | Code to connected; states connected/failed/expired
Y | P1 | Connecting | Downloadable bundle | Zip + per-OS launcher; superseded by install-once, kept as first-install fallback only | Built (fallback) | P1 | pairing | Download, double-click, connected
Y | P1 | Connecting | Local supervisor | Runs all your agents, checks prereqs, restarts on crash | Built | P2 | pairing | Agents survive a crash; clear skip reasons
Y | P1 | Connecting | Connect/disconnect UI | Connect/disconnect any agent from the GUI + dashboard | Built | P1 | liveness | GUI connect + disconnect both work
| P1 | Connecting | Install-once connector | Install once; join any room via a browser pairing code - no zip per join | Planned | P2 | pairing | A second join needs no re-download
| P1 | Connecting | Browser pairing | Paste the code in the browser; connector picks it up, no terminal/launcher | In progress | P2 | pairing | Pairing completes from the browser
| P1 | Connecting | Connector self-update | The installed connector updates itself; no stale re-fetch | Planned | P2 | install-once | Connector updates without a re-download
| P1 | Engagement | Engagement rules | Replies on @mention / engaged thread; quiet in chatter | In progress | P2 | connector | Follow-ups need no re-mention; no self-loops
| P1 | Visibility | In-chat run log | Every command the AI runs shows as a step (no secrets) | In progress | P1 | action cards | A multi-step task shows its steps in chat
| P2 | The Room | Directory panel | Live list of who is connected (agent/owner/online) | In progress | P1 | liveness | Survives restart; live list + status
Y | P2 | Connecting | Liveness | Heartbeat to online/away/offline dot | Built | P2 | connector | Disconnect flips to offline instantly
| P2 | Connecting | Presence hardening | Fix finicky online/offline: supervise the heartbeat, tie it to WS health, push status not 4s polling | In progress | P2 | liveness | Never shows online while actually disconnected
Y | P2 | Engagement | Mute / channel off | Per-user mute; per-channel on/off; fail-closed | Built | P1 | slash cmds | Muted = silent unless directly @mentioned
| P2 | Authority | Authority gates | Who can approve/edit/mutate, enforced server-side | In progress | P1 | auth tiers | Gates fail-closed; verified per tier
Y | P2 | The Brain | The Gate to Archive | /wrap to proposal to authorized human approves to saved | Built | P1 | auth gates | Approved case is saved; provenance server-derived
Y | P2 | The Brain | The Dictionary | Searchable problem to cause to fix to provenance index | Built | P1 | Gate | An approved case is a searchable entry
| P2 | The Brain | Tiered memory | Conversation / facts / skills / findings kept in tiers | In progress | P1 | auth tiers | Gate is the only durable writer
| P2 | Skills | Layered skills | Core/workplace/personal/grown; room serves a skill list on connect | In progress | P2 | connector | Agent gets the workplace skill list on connect
Y | P2 | Skills | Skills gate | Room re-checks every skill server-side, rejects with reasons | Built | P1 | skills | Bad skills rejected with a clear reason
Y | P2 | Channels | Default channels | Setup creates welcome/features/code-review + welcome post | Built | P1 | slash cmds | /agora setup builds the channels
Y | P2 | Channels | Per-channel AI toggle | Turn the AI on/off in a channel | Built | P1 | slash cmds | Off = bot ignores that channel
| P2 | Quality | Cross-OS check harness | Auto-verify a skill works (or fails gracefully) on Win/macOS/Linux | In progress | P2 | skills gate | Same skill passes on all 3, recorded
| P3 | Orchestration | Case & task tracking | One coordinator owns start/stop/resume of AI tasks | In progress | P1 | contracts | Tasks resume after interrupt; checkpointed
| P3 | Orchestration | Resource locks | Two tasks cannot mutate the same thing; read-only runs free | Planned | P1 | case/task | Conflicting mutations serialize, no auto-retry
| P3 | Agents | Agent roles | An agent holds a job: orchestrator/debug/audit/CI/general | Planned | P2 | auth tiers | A bot can be assigned a role + scoped skills
| P3 | Agents | Orchestrator agent | Splits a request, dispatches to agents, merges results | Planned | P2 | roles + case/task | One request fans out and comes back merged
Y | P3 | Agents | Private workspace | Each agent works in its own folder/config, separate from shared code | Built | P2 | adapters | Agent picks up its own folder config
Y | P3 | Codespace IDE | Host-backed git | Edit a real repo on a member machine via the room | Built | P3 | connector + auth | Browse/edit/commit/push a real repo
| P3 | Codespace IDE | Real-time editing | Several people edit the SAME file at once, merges live | Planned | P3 | host-backed git | Two browsers edit one file, it converges
| P3 | Codespace IDE | Live cursors | See where teammates are typing | Planned | P3 | real-time editing | Cursors/selection show per user
| P3 | Codespace IDE | Save to git | Live edits flush to disk; commit/push on demand | Planned | P3 | real-time editing | Edits land on the host git repo
| P3 | Codespace IDE | Live edit attribution (blame) | Every line shows who last changed it - a human user or which AI bot - from the realtime edit origin (not just at commit) | Planned | P3 | real-time editing | Hovering a line shows who last edited it + when
| P3 | Codespace IDE | Author coloring overlay | Toggle to tint text by author, like Google Docs 'edits by person' | Planned | P3 | live edit attribution | Toggle colors each author text distinctly
| P3 | Codespace IDE | Presence avatars + follow | See who is in the file; click an avatar to follow their viewport/cursor | Planned | P3 | live cursors | Avatars show; follow jumps to their cursor
| P3 | Visibility | Error transparency | On failure, chat shows which command failed + the reason | Planned | P1 | run log | No silent failures; typed reason in chat
| P3 | Visibility | Live state | Card shows running/done/failed/paused + health dot | In progress | P1 | run log | State always visible to the user
| P3 | The Room | Console panels | RHS: live action / brain browser / approval queue (polished) | In progress | P1 | action cards + brain | A promotion can be approved from the panel
| P4 | Skills | Cross-OS skills | One skill resolves the right tool per OS | In progress | P2 | skills | ssh-access runs from Windows AND Linux
| P4 | Skills | ssh-access + fleet-ops | The skills for the read-only robot-ops demo | Planned | P2 | cross-OS skills | Read-only ops diagnosis runs via the skill
| P4 | Agents | Dedicated channel agents | Debug / audit (cited) / CI-CD agents, each in its channel | Planned | P2 | roles | Each engages on its channel, scoped skills
| P4 | Orchestration | Agent overlap handling | Orchestrator spots two agents on the same area, serializes/warns | Planned | P1 | locks + orchestrator | Overlap gets serialized or a public warning
| P4 | Codespace IDE | Directory tree | Folder sidebar: expand, create, rename, delete files/folders | In progress | P3 | host-backed git | Full file/folder CRUD over host disk
| P4 | Codespace IDE | Rules engine | Enforce edit/commit/push rights, protected paths, commit msgs | Planned | P3 | real-time editing + auth | A rule reject gives a clear inline reason
| P4 | Codespace IDE | Speed & comfort | Instant local typing; no lost keystrokes on reconnect; offline banner | Planned | P3 | real-time + cursors | Under 50ms local echo; clean reconnect merge
Y | P4 | Codespace IDE | Agent writes here | A channel AI writes code into the shared codespace, live | Built | P2 | host-backed git + bind | Agent code blocks appear in the editor
| P4 | Codespace IDE | Who-wrote-this + why | Select a range to see last editor, time, and (if AI) the case/prompt that produced it - links back to chat | Planned | P3 | live edit attribution + run log | An AI-written line links back to its chat case
| P4 | Codespace IDE | Version history (timeline) | Google-Docs-style scrubber of named snapshots; open the file/codespace at any past point | Planned | P3 | real-time editing | You can open and read any past version
| P4 | Codespace IDE | Diff between versions | See what changed, and by whom, between two points in history | Planned | P3 | version history | Inline/side-by-side diff with per-author marks
| P4 | Codespace IDE | Restore / revert | Restore a past version, or revert one author change; rules-gated | Planned | P3 | version history + rules engine | Restore is recorded as a new attributed change
| P4 | Codespace IDE | Activity feed | Chronological per-file/codespace log: edits, commits, create/rename/delete, by whom | Planned | P3 | live edit attribution | A readable 'who did what when' timeline
| P4 | Codespace IDE | Commit co-authorship | On commit, record the humans + AIs whose edits are in it (Co-authored-by/manifest) so downstream git blame keeps the attribution | Planned | P3 | save to git + live edit attribution | A commit lists its real human + AI co-authors
| P4 | Codespace IDE | Durable attribution log | Append-only server-side record of every edit/commit with author + time (feeds the audit agent) | Planned | P3 | live edit attribution | Every edit/commit is in an immutable server log
| P4 | Codespace IDE | Inline comments | Google-Docs-style comments on a line/range, threaded and resolvable | Planned | P3 | real-time editing | Comment on a selection and resolve it
| P4 | Codespace IDE | @mention in code/comments | Ping a teammate or an AI from a comment; it posts to chat with a deep-link | Planned | P3 | inline comments | @mention notifies + links to the exact spot
| P4 | Codespace IDE | Soft file/range locks | Claim a file or region to avoid churn; others get a non-blocking warning | Planned | P3 | rules engine | A locked region warns others before they edit
| P4 | Codespace IDE | Find across codespace | Search all files in the codespace (server-side over host disk) | Planned | P3 | host-backed git | A query returns hits across files with paths
| P4 | Codespace IDE | Review before commit | Stage edits, review the diff, approve, then commit (rules + authority gated) | Planned | P3 | diff between versions + rules engine | A commit can require a reviewer
| P4 | Connecting | Cross-agent delegate | One person AI hands off to another (loop-protected) | Planned | P2 | pairing + orchestrator | Two agents delegate with hop-limit + cooldown
| P4 | The Brain | Distiller | Turns a case into a proposal; suggests update vs new | Planned | P2 | tiered memory | Proposes UPDATE vs CREATE, no duplicates
| P4 | Quality | End-to-end probes | Pass/fail test of the real flow per feature | In progress | P1 | - | Each feature has a live probe
| P4 | Quality | Clear error contracts | Skills/code return proper typed errors on bad input | In progress | P2 | probes | Bad input to enumerated typed error, no crash
| P4 | Quality | Graceful-failure tests | Verify reconnects, safe defaults, clean partial recovery | In progress | P1 | probes | Reconnect/backoff + fail-closed verified
| P5 | Later | Cross-use grants | Time-boxed consent to use another AI (Ask/Delegate/Drive) | Later | P1 | auth gates + delegate | Grant token authorizes; creds never transfer
| P5 | Later | Skill graduation | Lead promotes a grown skill to the shared set | Later | P2 | skills + compat | Graduates only after passing on all 3 OSes
| P5 | Later | Semantic search | Find related past cases by meaning (vector) | Later | P1 | tiered memory | Recall related cases without exact keywords
| P5 | Later | Sessions & modes | Group an AI session w/ mode (solo/co-op/debate/drive) | Later | P1 | case/task | A session holds participants + a mode
| P5 | Later | Timeline & decisions | Per-thread log of what happened + why | Later | P1 | run log + console | Replayable per-thread decision log
| P5 | Later | Codespace terminal | A safe sandboxed terminal per codespace | Later | P3 | host-backed git | Run commands in a per-codespace sandbox
| P5 | Later | Code language features (LSP) | Go-to-definition, hover types, lint in the editor via a language server | Later | P3 | real-time editing | Go-to-def + hover work in a file
| P5 | Later | CI/CD check agent | Watches a repo, runs build+test+lint+compat, posts pass/fail | Later | P2 | channel agents + probes | Posts a pass/fail action with logs in chat
| P5 | Later | Full white-label | Login page, favicon, every string - now folded into the P0 full rebrand (owning the fork) | In progress | P1 | branding | Zero Mattermost strings anywhere
| P5 | Later | Scheduler | Time/condition triggers, restart-safe, missed-fire policy | Later | P2 | - | at/every/after/deadline fire reliably

## Guide
Agora - Feature Checklist
How to read this
Done? | Mark Y when the feature is finished. Already-built features are pre-marked.
Phase | Build order. Each phase builds on the one before; within a phase, work runs in parallel.
Status | Built = working & verified. In progress = partly there. Planned = v1.0. Later = after v1.0.
Suggested person | Who could build it (a suggestion, not a fixed assignment) - see below.
Depends on | What must exist first.
Done when | The acceptance check - when it counts as finished.
Suggested people (3)
P1 | The Room - the Mattermost plugin: chat surface, Console, authority, the brain/Dictionary, orchestration.
P2 | The Agents - everything on the user machine + the learning loop: connector, agent roles, skills, growth.
P3 | The Codespace IDE - the shared real-time editor: live code sync, git, directory tree, rules.
The phases
P0 | Foundations - freeze the contracts, authority tiers, branding.
P1 | Spine - room and agents talk: action cards, connector, pairing, engagement, run log.
P2 | Trust & knowledge - authority gates, directory, the Gate to Dictionary, skills, cross-OS checks.
P3 | Orchestration & IDE core - case/task tracking, agent roles, orchestrator, real-time codespace, error transparency.
P4 | The demo & headline - ssh-access, debug/audit/CI agents, overlap handling, IDE tree+rules+speed, probes.
P5 | Later - debate mode, drive grants, semantic search, scheduler, terminal, full white-label.
v1.0 is done when
A member local AI joins from any OS, then @their-agent runs a read-only ops check via ssh-access, it shows as a live action card, then /wrap, a Lead approves, and it lands in the shared Dictionary. Plus: two people editing one file live in the shared codespace, merged and saved to git.
The rules every feature follows
1 | Works on every OS, or fails with a clear typed error - never a crash, never a silent single-OS assumption.
2 | Secrets never reach the AI - resolved only at use time, never in prompts/messages/logs.
3 | Nothing is saved to the shared brain without a human approving it.
4 | Risky actions are guarded - read-only is free; changes lock, are not blindly retried; high-impact needs confirm + auto-undo.
5 | No silent failures - every error is surfaced with a clear, specific reason.
6 | No made-up critique - claims backed by the code or a cited practice.
7 | Everything is tested - unit tests AND a real end-to-end check. Done = the demo works.